## Milestones & Gantt
Phase | Focus Area | Start Week | End Week | Key Deliverables
**Phase 1** | Documents, Specs & UI/UX | Week 1 | Week 3 | BRD, FSD, RTM, Tech Specs, Figma mocks, High-Fidelity Responsive HTML/CSS Web prototypes, Mobile Layout Wireframes.
**Phase 2** | Backend & Database Design | Week 4 | Week 6 | FastAPI project structure, PostgreSQL schema, Redis Cache Setup, Dockerization, Mock platform APIs (Lazada/Shopee/TikTok).
**Phase 3** | Integration & Sync Logic | Week 7 | Week 9 | Master SKU linking engine, inventory auto-deduction flow, centralized commission calculator, bulk printing manager.
**Phase 4** | Automated QA & CI/CD | Week 10 | Week 12 | Behave BDD tests run via Selenium & Appium locally and via GitHub Actions workflows.

## RACI Responsibility
Deliverable | Product Manager | Backend Dev | Frontend Dev | QA Engineer
**BRD & FSD** | **A** | C | C | I
**UX/UI Prototypes** | C | I | **A** | I
**Database Schema** | C | **A** | I | C
**API Endpoints** | **A** | **A** | C | C
**Sync Engine** | I | **A** | I | C
**Behave QA Automation** | I | I | I | **A**
**CI/CD Integration** | **A** | C | I | C